## FunctionPoints
Module Name | Functionality/form | Estimated hours |  |  | Total Estimated Hours | Estimate Descripton
|  | Design | Backend | Unit testing
Login | Login | 1 | 1 |  |  | All sub-modules estimated based on time taken for login module in past projects.
| Forgot Password | 0.5 | 1
| Change Password | 0.5 | 1
| Total | 2 | 3 | 1 | 6
All sub-modules estimated based on time taken for registration module in past projects.
Registration
| Validations | 1 | 2
| Data Manipulation | 0.5 | 1
| Email verification | 0.5 | 1
| Total | 2 | 4 | 1 | 7
The estimated time is based on a previous project which included add, update, delete operations of students.
Attendance | Add | 1 | 1
| Delete | 0.5 | 1
| Update | 1 | 1
| View | 1 | 1
| Total | 3.5 | 5 | 1 | 8.5
The estimated time is based on a previous project which included add, update, delete operations of students.
Faculty | Add | 1 | 1
| Delete | 0.5 | 1
| Update | 1 | 1
| View | 1 | 1
| Total | 3.5 | 5 | 1 | 8.5
The estimated time is based on a previous project which included add, update, delete operations of students.
Student | Add | 1 | 2
| Delete | 0.5 | 1
| Update | 1 | 1
| View | 1 | 1
| Total | 3.5 | 5 | 1 | 9.5
Estimation same as the Add,Update Functionalities mentioned above.
Fee | Add | 1 | 1
| Delete | 0.5 | 0.5
| Update | 0.5 | 0.5
| View | 1 | 1
| Total | 3 | 3 | 1 | 7
The estimated time is based on a previous project which included add, update, delete operations of salary details of emloyee.
Salary | Add | 1 | 1
| Delete | 0.5 | 0.5
| Update | 1 | 0.5
| View | 1 | 1
| Total | 3.5 | 3 | 1 | 7.5
Estimation same as the Add,Update Functionalities mentioned above.
To do list | Add | 1 | 0.5
| Delete | 0.5 | 0.5
| Update | 1 | 0.5
| View | 1 | 0.5
| Total | 3.5 | 2 | 1 | 6.5
Estimation same as the Add,Update Functionalities mentioned above.
Announcement | Add | 1 | 0.5
| Delete | 0.5 | 0.5
| Update | 1 | 0.5
| View | 1 | 0.5
| Total | 3.5 | 2 | 1 | 6.5
Fetching of details has been done in past projects. Result Generation involves different criteria selection and so, data should be fetched for different conditions.
Result | Graph | 3 | 2
| View | 1 | 2 | 1
| Total | 4 | 4 | 1 | 5
The estimated time is based on a previous project which included add, update, delete operations of students.
Question Paper | Add | 1.5 | 1
| Delete | 0.5 | 1
| Update | 1 | 1
| Total | 3 | 3 | 1 | 7
Estimation is done by researching for different agorithms for filtering. Also considering picking random questions this will be a new challenge for the team.
Question Paper Generation | Subject Wise Sorting | 1.5 | 1
| Topic Wise Sorting | 1 | 1
| Difficulty Wise Sorting | 1 | 1
| Number of Question difficulty wise | 1.5 | 1.5
| Count | 1 | 1
| Pdf Convertor | 0.5 | 0.5
| Random algo | 1 | 1
| Total | 7.5 | 7 | 3 | 17.5
Estimation same as the Add,Update Functionalities mentioned above.
Batch | Add | 1 | 0.5
| Delete | 0.5 | 0.5
| Update | 1 | 0.5
| View | 1 | 0.5
| Total | 3.5 | 2 | 1 | 6.5
Estimation same as the Add,Update Functionalities mentioned above.
Subject | Add | 1 | 0.5
| Delete | 0.5 | 0.5
| Update | 1 | 0.5
| View | 1 | 0.5
| Total | 3.5 | 2 | 1 | 6.5
Estimation is done by researching about how to take online quiz, how to maintain timer etc.
Online Exam | Timer | 2 | 1
| Validations | 1 | 0.5
| Generate Result | 2 | 1
| Shuffling of Questions | 1 | 0.5
| Total | 6 | 3 | 2 | 11
Overall Estimation
Total Time since Commencement (13-01-2020) = 4.5 Months (135 days Approx till 31-5-2020)
| Exam Days + Internship Work + Online Lecture | 30
| Other Holidays and Fests | 10
| Days Left for work | 95
| Total no of work hours | 760 | Total work of 10 person in a day 8 hours (for 95 days)
| Feasibility study | 76 | 10% of total
| Requirement Phase | 114 | 10-15% of total
| Design Phase | 76 | 10% of total
| Coding Phase and Unit testing | 152 | Estimation based on above mentioned plan. (With learning - 152)
| System Testing Phase | 304 | 40% of total
| Deployment Phase | 38 | 5% of total
| Learning Technologies | 90 | For learning the language and skills. This will go hand in hand with coding phase
| Total for all phases | 760