## Sheet1
Risk Monitoring, Mitigation and Management Plan
S. No. | Risk Item | Description | Probability of Occurrence* | Impact* | Priority# | Risk Indicators | Mitigation Plan | Contingency Plan | Remarks
1 | Business and Product Risk | User Resistance to adapt our system | 0.5 | 2 | 1 | Unaware of the System | Try advertising and popularizing the product | Will go to Institution to advertise | The usage of the product will be derived only after its launch
2 | Product Risk | Not able to implement some of the functionalities due to lack of time. | 0.8 | 2 | 1.6 | Incompletion of project | Try being more realistic while planning | Will try to atleast complete basic fuctions | We ar sure that we will be able to finish most of the features mentioned
3 | Team Related Risk | Unavailability of team members due to unforeseeable and/or unavoidable circumstances. | 0.3 | 3 | 0.9 | Shift of work burden | Distributing work equally amongst all members | Will distribute work equally | If any unforeseen situation occurs we will rather take the work on us and let the person recover form the trauma
4 | Technological Risk | Undefined problems encountered at the server side. | 0.8 | 1 | 0.8 | Occurrence of errors | Try to get the issue resolved asap | Will try to get the server back to normal | Mostly will be able to solve any server side issues, because it normally does not occur
5 | Technological Risk | Undefined problems encountered at the runtime (on-going test) at client side. | 0.5 | 1 | 0.5 | Reduced Credibility | Keep a backup of code on other pc's | Will have a code ready on other pc's | We will firstly test the system and after that will launch it
6 | Technological Risk | Risk of obsoletion of the technologies our test tool uses. | 0.8 | 1 | 0.8 | Failure of project | Keeping our product updated | Will try and do what the competition does | We mostly have very less amount of competitiors, but will try to handle them with a sense of maturity
7 | Legal Risk | Issues encountered while submission or updation of test, which may lead to legal consequences. | 0.8 | 1 | 0.8 | Legal Consequences | Try to make a backup of data at all times | Will try to avoid any legal consequences | We do not wan to go into any legal consequences, so will have terms and conditions stated
8 | Technological Risk | User Experience problems encountered in different browsers and devices. | 0.3 | 3 | 0.9 | Redesign the front-end | Try to make a good and supportive design | Will update css file asap | We ware already planning to suport most of the browsers, so this will not be an option
9 | Support Risk | Uncertainty in addition of new modules after deployment. | 0.5 | 3 | 1.5 | Recode | Make the code editable | Will try to add the function by bruteforcing | We are coding in such a way that it can easily be edited in the future
10 | Support Risk | Unable to maintain the system due to large number of out-house modules. | 0.5 | 2 | 1 | Creation of new modules | Try to keep all modules self made | Will try and agree upon terms with client | We will provide all the type of support if required
|  | High | Medium | Low
| *Probability | 0.8 | 0.5 | 0.3
|  | Catastrophic | Nominal | Negligible
| *Impact | 1 | 2 | 3
| #Priority | = | Probability * Impact